## Slide 1
Monthly Portfolio Health Review
Professional Services — Client Program Portfolio
Reporting Period: June 5, 2026 – June 26, 2026 | Prepared for: Executive Sponsor Review
ILLUSTRATIVE — SYNTHETIC 4-WEEK DATASET (real client engagements below were single-snapshot exports; see README)

## Slide 2
Portfolio Snapshot
Where the portfolio stands as of the latest reporting week
Chart: 
| Red | Amber | Green
Projects | 1 | 1 | 1
3
Projects in Portfolio
1 (Meridian Data Migration)
Declining This Month
1 (Helix ERP Rollout)
Recovering This Month
4 of 12 project-weeks
Weeks w/ Negative Client Sentiment

## Slide 3
Trend Analysis: Direction Matters More Than a Snapshot
RAG trajectory across the last 4 weekly reporting cycles (2 = Green, 1 = Amber, 0 = Red)
Chart: 
| Wk 1 (June 5) | Wk 2 (June 12) | Wk 3 (June 19) | Wk 4 (June 26)
Cascade Vendor Onboarding | 1 | 1 | 1 | 1
Helix ERP Rollout | 0 | 1 | 1 | 2
Meridian Data Migration | 2 | 1 | 1 | 0
Cascade Vendor Onboarding — Stable
Trajectory: Amber → Amber → Amber → Amber. Held steady across all 4 reporting weeks at Amber.
Helix ERP Rollout — Recovering
Trajectory: Red → Amber → Amber → Green. Recovered after corrective action; now Green.
Meridian Data Migration — Declining
Trajectory: Green → Amber → Amber → Red. Critical milestone(s) late: Environment Build, Connector Cutover Readiness Review.

## Slide 4
Emerging Risks Across the Portfolio
Patterns that would be missed by reviewing each project in isolation
1
Third-Party / Resourcing Dependency Risk
3 of 3 active projects hit a dependency-related blocker this month — vendor/third-party dependency (Cascade Vendor Onboarding, Meridian Data Migration); resourcing/ownership gap (Helix ERP Rollout). Different root causes, same pattern: this is a portfolio-level delivery risk, not a one-off, and worth a standing vendor/resourcing escalation path rather than per-project firefighting.
2
Overspend Correlates With Schedule Slip
Meridian Data Migration's budget burn reached 135% of plan in the week ending 2026-06-26, the same week its overall status was Red — spend accelerating to chase a slipping date typically front-loads cost without recovering time.
3
Sentiment Is a Leading Indicator, Not a Lagging One
On Meridian Data Migration, client sentiment turned negative in the week ending 2026-06-12, 2 week(s) before the status flipped to Red on 2026-06-26. Treating sentiment dips as an early-warning trigger — not just a symptom — would buy real lead time portfolio-wide.

## Slide 5
Spotlight: Meridian Data Migration
STATUS: RED
Schedule
Critical milestone(s) late: Environment Build, Connector Cutover Readiness Review.
Budget
Spend is 135% of planned — significantly overspending.
Milestones
2 milestones are overdue: Environment Build, Connector Cutover Readiness Review.
Blockers
Critical blocker(s) open: Critical: vendor unable to deliver API access, now directly blocking cutover readiness.
Sentiment
Stakeholder tone is negative and worsening.
Bottom line for the client conversation
Critical milestone(s) late: Environment Build, Connector Cutover Readiness Review. This requires executive-level attention this cycle — Escalate the open blocker(s) to the steering committee this week; they are the primary driver of risk.

## Slide 6
Executive Recommendations
Actions for this coming month, in priority order
1
Address the Meridian Data Migration schedule issue this week
Critical milestone(s) late: Environment Build, Connector Cutover Readiness Review.
2
Act on: Third-Party / Resourcing Dependency Risk
3 of 3 active projects hit a dependency-related blocker this month — vendor/third-party dependency (Cascade Vendor Onboarding, Meridian Data Migration); resourcing/ownership gap (Helix ERP Rollout). Different root causes, same pattern: this is a portfolio-level delivery risk, not a one-off, and worth a standing vendor/resourcing escalation path rather than per-project firefighting.
3
Act on: Overspend Correlates With Schedule Slip
Meridian Data Migration's budget burn reached 135% of plan in the week ending 2026-06-26, the same week its overall status was Red — spend accelerating to chase a slipping date typically front-loads cost without recovering time.
4
Act on: Sentiment Is a Leading Indicator, Not a Lagging One
On Meridian Data Migration, client sentiment turned negative in the week ending 2026-06-12, 2 week(s) before the status flipped to Red on 2026-06-26. Treating sentiment dips as an early-warning trigger — not just a symptom — would buy real lead time portfolio-wide.
5
Use Helix ERP Rollout's recovery as an internal playbook
Document what specifically reversed the decline so other PMs facing similar risk patterns can apply it faster.

## Slide 7
Appendix: How RAG Status Is Determined
Automated weekly scoring across five weighted signals, with escalation overrides
Schedule (25%)
% of tasks past their planned date; any late critical milestone forces Red.
Budget (20%)
Actual vs. planned spend-to-date. Green 90–110%, Amber 70–90% / 110–130%, Red beyond that.
Milestones (25%)
Overdue milestones and those due within 2 weeks flagged at risk.
Blockers (20%)
Count, severity, and age of open blockers; any critical or 14+ day blocker escalates.
Sentiment (10%)
PM/client narrative tone and week-over-week trend, classified automatically.
Missing data is never treated as automatically Green — it is scored Amber and flagged for follow-up. Critical blockers or 2+ overdue milestones override the weighted score and force Red regardless of other signals.
Full methodology: RAG_METHODOLOGY.md | Agent source: /agent | Weekly reports: /outputs/weekly_demo